## Schedule
Election Forecast — Live-Readiness Schedule for Nov 3, 2026
Work starts Thursday, July 9, 2026. Red = critical path. Orange = fixed, irreplaceable deadline (primary/election).
ID | Phase | Task | Start | Due | Days | Priority | Depends On | Status | Notes
PHASE A — FOUNDATION (before AZ primary — CRITICAL PATH)
1 | A | Lock down CORS on Render (env CORS_ORIGINS = Vercel URL) | 2026-07-09 | 2026-07-09 |  | Quick | - | Not started | 5-min wrap-up from Phase 7 deploy
2 | A | Feed audit round 2 — confirm each state's live ENR URL + format | 2026-07-09 | 2026-07-11 |  | High | - | Not started | See FEED_AUDIT.md
3 | A | Beat the Clarity 403 (browser-faithful fetch -> Playwright fallback) | 2026-07-09 | 2026-07-16 |  | CRITICAL | - | Not started | Gates GA/PA/TX/MI live feeds (Issue #1)
4 | A | Build NC county ingestor (non-Clarity; easiest; by-voting-method) | 2026-07-09 | 2026-07-14 |  | CRITICAL | - | Not started | Proves the county-level pattern
5 | A | Build AZ county reader + dry-run vs archives | 2026-07-15 | 2026-07-20 |  | CRITICAL | 3 | Not started | Must be ready for Jul 21
|  |  | 2026-07-21 | AZ PRIMARY — LIVE TEST #1: pull AZ county feed end-to-end (irreplaceable window)
PHASE B — MI PREP
6 | B | Fix issues the AZ test surfaced | 2026-07-22 | 2026-07-25 |  | High | AZ test | Not started
7 | B | MI per-county Clarity discovery (county totals) | 2026-07-26 | 2026-08-01 |  | High | 3 | Not started
|  |  | 2026-08-04 | MI PRIMARY — LIVE TEST #2: per-county Clarity discovery
PHASE C — WI PREP
8 | C | Fill MI 2026 nominees in api/elections.py (known after Aug 4) | 2026-08-05 | 2026-08-05 |  | Quick | MI primary | Not started | 1-line edit
9 | C | Build WI county-level ingestor (72 county clerk sites / AP-aggregated) | 2026-08-05 | 2026-08-10 |  | High | - | Not started | Hardest — no statewide feed
|  |  | 2026-08-11 | WI PRIMARY — LIVE TEST #3: WI at county level
PHASE D — HARDEN (Aug–Sep)
10 | D | Finish remaining county ingestors: GA, PA, TX, NV | 2026-08-12 | 2026-09-05 |  | High | 3 | Not started
11 | D | Test no-primary states (NV/NC/PA/TX/GA) vs archives/specials | 2026-08-12 | 2026-09-15 |  | Med | - | Not started
12 | D | Wire live poller as prod background worker (replaces 'Next Batch') | 2026-09-01 | 2026-09-20 |  | High | - | Not started
13 | D | Load 2022 Senate data (for general2028 stub) | 2026-09-08 | 2026-09-12 |  | Low | - | Not started
14 | D | Upgrade Render -> Starter ($7/mo) + persistent disk | 2026-09-20 | 2026-09-25 |  | Med | - | Not started | Avoids cold-start DB re-download
PHASE E — PRE-ELECTION (Oct)
15 | E | Election-ID auto-discovery | 2026-10-01 | 2026-10-10 |  | High | - | Not started | States publish Nov IDs shortly before
16 | E | SQLite -> Postgres if load warrants (optional) | 2026-10-10 | 2026-10-15 |  | Low | - | Not started
17 | E | Monitoring + alerting setup | 2026-10-10 | 2026-10-20 |  | Med | - | Not started
PHASE F — FINAL (late Oct → Nov 2)
18 | F | Capture real 2026 election IDs as states publish | 2026-10-21 | 2026-11-01 |  | CRITICAL | - | Not started | Ongoing as states publish
19 | F | Full dry-run vs live (0%-reported) feeds end-to-end | 2026-10-26 | 2026-10-30 |  | CRITICAL | 18 | Not started
20 | F | Final rehearsal + on-call / monitoring plan | 2026-11-01 | 2026-11-02 |  | High | - | Not started
|  |  | 2026-11-03 | ELECTION NIGHT — GO LIVE

## Key Dates
Milestone | Date | Notes | Days away
Work starts | 2026-07-09 | Begin Phase A (critical path)
AZ primary — live test #1 | 2026-07-21 | Must have Clarity-403 fix + a county ingestor ready
MI primary — live test #2 | 2026-08-04 | MI nominees decided here
WI primary — live test #3 | 2026-08-11 | Hardest state (no statewide feed)
ELECTION NIGHT — go live | 2026-11-03 | Senate Class-2: GA/MI/NC/TX (no President in 2026)
Formulas:
Days away = [Date]-TODAY()